## ProjectSchedule
Screenwriting Project Gantt Chart | [5 empty] | ► Watch How to Make a Gantt Chart in Excel
| Project Start: | 2026-01-19
| Today: | 2026-04-28
| Display Week: | 1 |  |  | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04
 | time axis 2026-01-19 to 2026-05-10
TASK | PROGRESS | START | END | DAYS | time axis 2026-01-19 to 2026-05-10
Phase 1 | bar: 2026-01-19 to 2026-02-13
General Screenwriting Research | 100% | 2026-01-19 | 2026-01-29 | 11
Final Draft Research | 100% | 2026-01-24 | 2026-01-25 | 2
Celx Research | 100% | 2026-01-25 | 2026-01-26 | 2
Fade In Research | 100% | 2026-01-26 | 2026-01-27 | 2
Arc Studio Research | 100% | 2026-01-27 | 2026-01-28 | 2
Scrivener Research | 100% | 2026-01-28 | 2026-01-29 | 2
Survey | 100% | 2026-01-29 | 2026-02-05 | 8
Test Project | 100% | 2026-02-01 | 2026-02-11 | 11
Goals and Objectives | 100% | 2026-02-06 | 2026-02-12 | 7
First Report Deadline | 100% | 2026-02-07 | 2026-02-13 | 7 | bar: 2026-02-13
Phase 2 | bar: 2026-02-14 to 2026-04-20
Project Skeleton | 100% | 2026-02-14 | 2026-04-20 | 66
Increment #1 (Model Layer) | 100% | 2026-02-14 | 2026-04-20 | 66
Increment #2 (ViewModel + OSF) | 100% | 2026-02-14 | 2026-04-20 | 66
Increment #3 (ScriptEditor + Scene Navigator) | 100% | 2026-02-14 | 2026-04-20 | 66
Increment #4 (Pdf Export + Bug Fixes) | 100% | 2026-02-14 | 2026-04-20 | 66
Phase 3 Title
Report | 90% | 2026-04-20 | 2026-05-01 | 12
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.